## Sheet1
Project Management Log
Course: Front End Application Development
Project Name: Build a bug reporting system
Task | Start Date | End Date
Requirements Analysis and Revision of Lectures | 12.04.21 | 16.04.21
Looking after and testing available APIs with Postman | 17.04.21 | 18.04.21
Definition of Model | 19.04.21 | 19.04.21
Set navigation bar and routing | 19.04.21 | 19.04.21
Bug List Page Creation - styling | 20.04.21 | 21.04.21
Definition of functions GET and GET by id, POST, PUT, DELETE in service | 22.04.21 | 22.04.21
Get all bugs, get bug by id and delete bugs in bug list page, test with Postman | 23.04.21 | 25.04.21
Update Bug Form Creation - styling | 10.05.21 | 10.05.21
Create Bug Form Creation - styling | 10.05.21 | 10.05.21
Update (PUT) bugs in update bug page, test with Postman | 11.05.21 | 11.05.21
Create (POST) bugs in report bug page, test with Postman | 12.05.21 | 12.05.21
Validate forms, set snackbar and style it | 13.05.21 | 13.05.21
Work on getting bug comments, adding new comments, deleting comments, test with Postman | 14.05.21 | 16.05.21
Sort data in Bug List Table, test with Postman | 17.05.21 | 17.05.21
Get all bugs and not 10 by default, test with Postman | 18.05.21 | 18.05.21
Implement data pagination in Bug List Table, test with Postman | 18.05.21 | 19.05.21
Implement advanced search in Bug List Table, test with Postman | 20.05.21 | 22.05.21
Look after style modification and web responsiveness, test with ResponsivelyApp | 23.05.21 | 23.05.21
Revision of code structure, clearness, comments and indentation | 23.05.21 | 24.05.21
Write Report | 25.05.21 | 27.05.21